## Metrics
Metrics | Risk Measured | Frequency of Measurement | Formula |  | Legends
[5 empty] | Green | Value>=0
Schedule | This metric measures the Team's Ability to meet the committed Release | Weekly | Schedule Risk Score = remaing # of sprints for release-# of sprint for last pass(team specific)-(Pending user story points for the release/Average velocity) |  | Yellow | -1.0<Value<0
[5 empty] | Red | Value<=-1.0
Note: Average velocity = Sum of last 6 sprints velocity / 6
[5 empty] | Green | Until scope touches 90% of the planned capacity for the release
Scope | This metric measures the Variance in the committed story points for the upcoming release with updated data taken periodically | Weekly | Scope = # of story points committed for the release(based on the grooming per sprint)/planned capacity for the release(in story points)*100 |  | Yellow | When scope story points is between 90 and 95% of planned capacity
[5 empty] | Red | When scope story points is above 95%
Quality | This metric measures the quality of feature delivered |  | Jira extracted data for each of the below Parameter Values for each of the LOB.
Parameters
|  | Daily | Requirement Test Coverage = (# of BDD+Manual Scenarios Tested)/(Total # of BDD+Manual Scenarios Planned) |  | Green | Refer Requirement Test Coverage sheet
Yellow
Red
|  | Daily | Insprint Observations |  | Green | Value<=0.2
[5 empty] | Yellow | 0.2<Value<0.5
[5 empty] | Red | Value>=0.5
|  | Once at end of Sprint | Defect Leakage QA = 0.4*# of Defects found in RIT+0.6*# of defects found in Pre-Prod |  | Green | Value <=0.2
[5 empty] | Yellow | 0.2<Value<0.5
[5 empty] | Red | Value>=0.5
|  | Once at end of Sprint | Production Defect = 0.5* # of Sev1 Defects +0.3* # of Sev2 defects + 0.2*# of Sev3 defects |  | Green | Value <=0.2
[5 empty] | Red | Value>0.2
Quality Engineering practice | This is a combination of UI (visual) defects and Functinal defects where each of the defects will be calculated on TDD coverage (in %) and BDD (# of scenario)
Paramaters
|  | Once at end of Sprint | TDD coverage (in %) which covers Repository, Web Api and UI test coverage |  | Green | Value=>95%
[5 empty] | Yellow | 80%<Value<=95%
[5 empty] | Red | Value<80%
|  | Once at end of Sprint | BDD Coverage (in number of scenario automated/Total # of scenarios) |  | Green | Value=>80%
[5 empty] | Yellow | 80%<Value<=65%
[5 empty] | Red | Value<65%
|  | Once at end of Sprint | MVP Adoption(# of Releases/Half-Year) |  | Green | Value=>2
[5 empty] | Yellow | Value=1
[5 empty] | Red | Value<=0
|  | Once at end of Sprint | Code Review- Dev |  | Green | Catastrophic, Major, Minor Defect =0
[5 empty] | Yellow | Catastrophic and Major Defects without workaround =0 & 0<Major Defects with workaround <5
[5 empty] | Red | Catastrophic or Major Defects without workaround >0 or Major Defects with workaround >5
|  | Once at end of Sprint | Code Review-QA |  | Green | Catastrophic, Major, Minor Defect =0
[5 empty] | Yellow | Catastrophic and Major Defects without workaround =0 & 0<Major Defects with workaround <5
[5 empty] | Red | Catastrophic or Major Defects without workaround >0
|  | Once at end of Sprint | Maintainability Index |  | Green | MI>=60
[5 empty] | Red | MI<60
|  | Once at end of Sprint | Cyclomatic Complexity |  | Green | CC<=15
[5 empty] | Red | CC>15
SLA | SLA is a combination of all the parameters that get communicated to the Vendor Management team against each of the Work Orders. This would vary across LOBs | Monthly | Manual Entry of the Parameter Values for each of the LOB. |  | Green | When all parameters are in Green
[5 empty] | Yellow | When one or more parameters are in yellow
[5 empty] | Red | When one or more parameters are in Red
|  |  | SLA Parameters | Target Value per WO
|  |  | Schedule Adherence | >95% | Green | Value = 100%
[5 empty] | Yellow | 95%<=Value<100%
[5 empty] | Red | Value< 95%
|  |  | Defect Density-Non-Prod | <0.4 | Green | Value<0.2
[5 empty] | Yellow | 0.2<Value<=0.4
[5 empty] | Red | 0.4<Value
|  |  | Sev1 Defect Leakage - Non Prod | 0 | Green | Value=0
[5 empty] | Red | Value=!0
|  |  | Defect Density-Prod | <0.02 | Green | Value<0.01
[5 empty] | Yellow | 0.01<Value<=0.02
[5 empty] | Red | 0.02<Value
|  |  | Sev1 Defect Leakage - Prod | 0 | Green | Value=0
[5 empty] | Red | Value=!0
|  |  | Sev2 Defect Leakage - Prod | 0 | Green | Value=0
[5 empty] | Red | Value=!0
|  |  | Defect Rejection Rate | <10% | Green | Value<10%
[5 empty] | Yellow | 5%<Value<=10%
[5 empty] | Red | 10%<Value
|  | Monthly | Manual Entry of the Parameter Values for each of the LOB. |  | Green | When all parameters are in Green
Resource | To identify resource related risks |  |  |  | Yellow | When one or more parameters are in yellow
[5 empty] | Red | When one or more parameters are in Red
|  | Monthly | Attrition |  | Green | Value=0
[5 empty] | Yellow | 0<Value<=1
[5 empty] | Red | 1<Value
|  | Monthly | Availability of Resource with Required Skillset |  | Green | Value='Yes'
[5 empty] | Yellow | Value='Partial'
[5 empty] | Red | Value='No'

## Requirement Test Coverage
# of Scenarios (Total) | 10 | 5 | 5
# of Scenarios BDD Tested | 6
# of Scenarios Manually Tested | 0
Sprint End Date (MM/DD/YYYY) | 2017-06-06
No. of Days remaing for Sprint Completion | 3
No. of Days in a Sprint | 10
Pending Test Coverage | Days Left Index (Days Remaining in Sprint/No. of Days in sprint)
0.4 | 0.3
Green | -0.1
Green | Day 1 to 5 of sprint or (Days Left Index-Pending Test Coverage>=0)
Amber | 0>Days Left Index-Pending Test Coverage>=-0.1
Red | -0.1>Days Left Index-Pending Test Coverage