## Slide 1
EAC, SAC
Weekly Dashboard Mar 24, 2017
Overall Status
# | Schwab BU | Program | Owner(s) | Team Size | Scope | Schedule | Quality | Cost | Resource | SLA | Compliance | Productivity | Remarks
1 | Investor Services (Retail) | Equity Award Center (EAC) [Pankaj/Jay] | Shafi/ Babu | 33 |  |  |  |  |  |  |  |  | Integration issue - Pankaj *1
2 | Investor Services (Retail) | SPS [Steve/Nate] | Manoj/ Anu | 1+6 = 7 |  |  |  |  |  |  |  |  | Merge issue – Andy Gray *2
3 | Adviser Services (SAC) | Top Pain Points [Andy Gray] | Ritika/ Anu | 1+3 = 4 |  |  |  |  |  |  |  |  | Merge issue – Andy Gray *2
4 | Adviser Services (SAC) | eSignature Offering/ Paperless [Andy Gray] | Prasanth/ Anu | 1+6=7 |  |  |  |  |  |  |  |  | 
5 | Adviser Services (SAC) | Action Center [Nancy] | Babu/ Yogesh |  |  |  |  |  |  |  |  |  | 
6 | Adviser Services (SAC) | Gateway Services [?] | Babu/ Yogesh |  |  |  |  |  |  |  |  |  | 
7 | Adviser Services (SAC) | Move Money [Andy Gray] | Swapnil/ Anu | 1+3 = 4 |  |  |  |  |  |  |  |  | SLA/quality issue
8 | Adviser Services (SAC) | Portfolio Connect [?] | Anup Mathew | 1+3=4 |  |  |  |  |  |  |  |  | 
Program-wise Status
Risks/Issues/Dependencies/Concerns
# | Type | Description | Owner | Exposure/ Severity | Status
1 | Issue | EAC: PROD release on 17-May-2017 has dependencies with other Schwab/vendor work streams and due to their delay in completing the sprints/features, it could cause delay in our OWNED release. | Babu | Medium | In Progress
2 | Issue | SAC – Top Pain Points – Merge issue from Andy – offshore team needs to start merging the code and take ownership. | Babu | Medium | In Progress
G
Revenue
G
Margin
Y
Schedule
Y
Quality
Green | 
Yellow | 3
Red | 
Projects
Y
SLA
G
Compliance
Y
Productivity

## Slide 2
Equity Award Center (EAC) Integration
Weekly Status Report Mar 24, 2017
Highlights
Accomplishments | In Progress | Upcoming Milestones
Completed … | In Progress | Upcoming
Risks/Issues/Dependencies
# | Type | Description | Owner | Exposure/ Severity | Status
Overall Status
Timelines
Program/Release Contacts
# | Role | Name
1 | Business Sponsor | Kate O’Connor
2 | IT Sponsor | Pankaj Jain
3 | Program Manager | Adam Charles
4 | Product Owner | Lara Andrews
5 | Project Manager | Martin Gair
6 | Mphasis Contact | Babu Mani
7 | BSA | 
Cost
Schedule
Quality
G
Y
G
Yellow
Y
Scope
Work Stream | Sprint Completion 4/19 | Code Freeze 4/20 | Rel. Integration 4/24 | UAT 5/4 | Pre-prod 5/8 | PROD 5/17
EAC Big Web
EAC Mobile Web
Global – Mobile Web
Global – Big Web
SPS
On Track
Risk/ Issue
Critical
Not Started
Release Progression - May’17